## SUMSHEET
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
SUMMARY SHEET
(2014--2018)
| FUNDING | 2014 | 2015 | 2016 | 2017 | 2018 | TOTALS
| BOND | 0 | 5701000 | 0 | 5327700 | 0 | 11028700
| BOND (2013) | 2643050 | 0 | 0 | 0 | 0 | 2643050
| BOND (2009) | 10000 | 0 | 0 | 0 | 0 | 10000
| CDBG | 546882 | 597000 | 482000 | 541000 | 245000 | 2411882
| FEDERAL | 3844992 | 1268203 | 0 | 600000 | 1200000 | 6913195
| STATE | 1554455 | 400000 | 0 | 0 | 0 | 1954455
| LIQUID FUELS | 877058 | 1461750 | 840000 | 855000 | 620000 | 4653808
| FEMA/PEMA | 271000 | 0 | 0 | 0 | 0 | 271000
| ACT 56 | 0 | 375000 | 0 | 0 | 0 | 375000
| OTHER | 923226 | 718019 | 1632500 | 574000 | 1637000 | 5484745
| COUNTY | 386589 | 0 | 0 | 0 | 0 | 386589
| TOTALS | 11057252 | 10520972 | 2954500 | 7897700 | 3702000 | 36132424
| SPENDING | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SCHEDULE | 10257252 | 9843472 | 4432000 | 6472700 | 5127000 | 36132424
LAST REVISED 09/16/13

## Public Safety
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE 2014-2018
PUBLIC SAFETY
PROJECT |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
DESCRIPTION
1. Ambulance Replacement/Remount Plan | SPENDING SCHEDULE |  | 135000 | 135000 | 135000 | 135000 | 540000
FUNDING
| BOND |  | 75000 |  | 75000 |  | 150000
| OTHER |  |  | 135000 |  | 135000 | 270000
| CDBG |  | 60000 |  | 60000 |  | 120000
2. Flood Control System | SPENDING SCHEDULE |  |  |  | 600000 | 1200000 | 1800000
| FUNDING | [5 empty] | 0
| FEDERAL |  |  |  | 600000 | 1200000 | 1800000
3. Fire Apparatus Replacement Plan | SPENDING SCHEDULE |  | 1000000 |  | 250000 |  | 1250000
FUNDING
| BOND |  | 1000000 |  | 250000 |  | 1250000
4. Replacement of 911 Radio System | SPENDING SCHEDULE |  |  |  | 250000 |  | 250000
Microwave Links | FUNDING
| BOND |  |  |  | 250000 |  | 250000
5. 911 Radio System Software Upgrade | SPENDING SCHEDULE |  | 750000 |  |  |  | 750000
from 7.7 to 7.14 | FUNDING
| ACT 56 |  | 375000 |  |  |  | 375000
| BOND |  | 375000 |  |  |  | 375000
PUBLIC SAFETY |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 0 | 1885000 | 135000 | 1235000 | 1335000 | 4590000
FUNDING
| BOND | 0 | 1450000 | 0 | 575000 | 0 | 2025000
| ACT 56 | 0 | 375000 | 0 | 0 | 0 | 375000
| CDBG | 0 | 60000 | 0 | 60000 | 0 | 120000
| OTHER | 0 | 0 | 135000 | 0 | 135000 | 270000
| FEDERAL |  |  |  | 600000 | 1200000 | 1800000
| TOTALS | 0 | 1885000 | 135000 | 1235000 | 1335000 | 4590000

## P W Traffic
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - TRAFFIC
PROJECT |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
DESCRIPTION
1. TR/Isolated Intersections | SPENDING SCHEDULE | 164150 | 100000 | 100000 | 100000 | 100000 | 564150
FUNDING
| BOND (2013) | 164150 |  |  |  |  | 164150
| BOND |  | 200000 |  | 200000 |  | 400000
2. TR/Traffic Safety Imprv. | SPENDING SCHEDULE | 38500 | 37500 | 37500 | 37500 | 37500 | 188500
FUNDING
| BOND 2013 | 38500 |  |  |  |  | 38500
| BOND |  | 75000 |  | 75000 |  | 150000
PUBLIC WORKS-TRAFFIC |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 202650 | 137500 | 137500 | 137500 | 137500 | 752650
FUNDING
| BOND 2013 | 202650 | 0 | 0 | 0 | 0 | 202650
| BOND | 0 | 275000 | 0 | 275000 | 0 | 550000
| TOTALS | 202650 | 275000 | 0 | 275000 | 0 | 752650

## P W Streets
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS--STREETS
PROJECT
DESCRIPTION |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
1. North Street | SPENDING SCHEDULE | 420000 |  |  |  |  | 420000
New St. to Center St. | FUNDING
(Roadway and Service | BOND (2013) | 310000 |  |  |  |  | 310000
| CDBG | 110000 |  |  |  |  | 110000
2. Carlton Avenue | SPENDING SCHEDULE |  | 237000 | 237000 | 236000 |  | 710000
Broadway to Summit St. | FUNDING
| CDBG |  | 237000 | 237000 | 236000 |  | 710000
3. West Packer Ave | SPENDING SCHEDULE |  |  |  | 180000 | 142000 | 322000
Montclair Ave to Brodhead Ave | FUNDING
| OTHER |  |  |  | 180000 | 142000 | 322000
4. West Packer Avenue | SPENDING SCHEDULE |  |  | 219000 |  |  | 219000
Carlton to Montclair | FUNDING
| OTHER |  |  | 219000 |  |  | 219000
5. Public Works Engineering | SPENDING SCHEDULE | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
Costs for CDBG Eligible | FUNDING
Street Projects | CDBG | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
6. West Garrison Street | SPENDING SCHEDULE |  | 128000 |  |  |  | 128000
Main Street to N. New Street | FUNDING
| BOND |  | 128000 |  |  |  | 128000
| BOND |  | 128000 |  |  |  | 128000
7. E. 5th Street | SPENDING SCHEDULE |  |  |  | 200000 | 195000 | 395000
William to Arnold | FUNDING
| OTHER |  |  |  | 200000 | 195000 | 395000
8. City Hall Complex Parking | SPENDING SCHEDULE |  | 135000 |  |  |  | 135000
Lay-bys Reconstruction | FUNDING
Phase III | BOND |  | 135000 |  |  |  | 135000
9. Fourth Avenue | SPENDING SCHEDULE |  |  | 50000 |  |  | 50000
Prospect Ave. to Kichline St. | FUNDING
| OTHER |  |  | 50000 |  |  | 50000
10. West Broad Street | SPENDING SCHEDULE |  |  | 50000 |  |  | 50000
(Mangan Street west to old Coke | FUNDING
Plant-curb and sidewalk) | OTHER |  |  | 50000 |  |  | 50000
11. 3rd & 4th Streets Streetscape/ | SPENDING SCHEDULE |  | 217000 | 221000 | 194000 | 165000 | 797000
Sidewalks | FUNDING
| OTHER |  | 217000 | 221000 | 194000 | 165000 | 797000
12. New Street - 3rd to 4th Streets | SPENDING SCHEDULE | 80000 |  |  |  |  | 80000
FUNDING
| OTHER | 80000 |  |  |  |  | 80000
PUBLIC WORKS STREETS |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 510000 | 727000 | 787000 | 820000 | 512000 | 3356000
FUNDING
| BOND (2013) | 310000 | 0 | 0 | 0 | 0 | 310000
| BOND | 0 | 263000 | 0 | 0 | 0 | 263000
| CDBG | 120000 | 247000 | 247000 | 246000 | 10000 | 870000
| OTHER | 80000 | 217000 | 540000 | 574000 | 502000 | 1913000
| TOTALS | 510000 | 727000 | 787000 | 820000 | 512000 | 3356000

## P W Storm Sewers
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS--STORM SEWERS
PROJECT
DESCRIPTION
|  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
1. Stefko Drainage Swale | SPENDING SCHEDULE | 150000 |  | 1000000 | 500000 |  | 1650000
FUNDING
| BOND |  |  |  | 250000 |  | 250000
| LIQUID FUELS |  |  | 250000 | 250000 |  | 500000
| OTHER | 150000 |  | 750000 |  |  | 900000
2. W. Goepp St. | SPENDING SCHEDULE |  | 250000 |  |  |  | 250000
Masslich Street to New | FUNDING
Street (Radley) | LIQUID FUELS | [5 empty] | 0
| BOND |  | 250000 |  |  |  | 250000
3. Old Brick Sewer | SPENDING SCHEDULE |  | 200000 |  |  |  | 200000
Jischke St to 3rd St | FUNDING
| LIQUID FUELS |  | 200000 |  |  |  | 200000
4. Johnston Drive | SPENDING SCHEDULE |  |  |  |  | 1000000 | 1000000
Swale Improvement | FUNDING
| OTHER |  |  |  |  | 1000000 | 1000000
5. West Laurel Street to | SPENDING SCHEDULE |  | 225000 |  |  |  | 225000
the Monocacy Creek | FUNDING
| LIQUID FUELS |  | 78750 |  |  |  | 78750
| OTHER (MORAV COL) |  | 146250 |  |  |  | 146250
6. East Boulevard | SPENDING SCHEDULE |  | 234000 |  |  |  | 234000
Boyd Street Southwardly | FUNDING
to Lansdale Avenue | LIQUID FUELS |  | 234000 |  |  |  | 234000
7. Linden Street Storm | SPENDING SCHEDULE | 317058 |  |  |  |  | 317058
Sewer Upgrade/Repl. | FUNDING
| LIQUID FUELS | 317058 |  |  |  |  | 317058
8. Fifth Street-Buchanan to | SPENDING SCHEDULE |  | 220000 |  |  |  | 220000
Fillmore | FUNDING
| LIQUID FUELS |  | 220000 |  |  |  | 220000
PUBLIC WORKS- |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
STORM SEWERS | SPENDING SCHEDULE | 467058 | 1129000 | 1000000 | 500000 | 1000000 | 4096058
FUNDING
| BOND | 0 | 250000 | 0 | 250000 | 0 | 500000
| LIQUID FUELS | 317058 | 732750 | 250000 | 250000 | 0 | 1549808
| OTHER | 150000 | 146250 | 750000 | 0 | 1000000 | 2046250
| TOTALS | 467058 | 1129000 | 1000000 | 500000 | 1000000 | 4096058

## P W Other
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS--OTHER PROJECTS
PROJECT
DESCRIPTION |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
1. Lynn Ave. Bridge | SPENDING SCHEDULE | 3573629 | 1100000 |  |  |  | 4673629
FUNDING
| CDBG | 178682 | 55000 |  |  |  | 233682
| FEDERAL | 2858903 | 880000 |  |  |  | 3738903
| STATE | 536044 | 165000 |  |  |  | 701044
2. High St. Bridge | SPENDING SCHEDULE | 636315 | 415472 |  |  |  | 1051787
FUNDING
| FEDERAL | 536089 | 388203 |  |  |  | 924292
| OTHER (RAILROAD) | 100226 | 27269 |  |  |  | 127495
3. Bridge Repair | SPENDING SCHEDULE | 60000 | 70000 | 70000 | 70000 | 70000 | 340000
FUNDING
| BOND 2013 | 60000 |  |  |  |  | 60000
| BOND |  | 140000 |  | 140000 |  | 280000
4. Main Street | SPENDING SCHEDULE | 500000 | 655000 | 415000 |  |  | 1570000
Streetscape | FUNDING
| BOND (2013) | 250000 |  |  |  |  | 250000
| BOND |  | 535000 |  |  |  | 535000
| OTHER | 250000 | 327500 | 207500 |  |  | 785000
5. Street Overlay | SPENDING SCHEDULE | 710000 | 700000 | 710000 | 870000 | 880000 | 3870000
Program | FUNDING
| BOND 2013 | 310000 |  |  |  |  | 310000
| BOND (2009) | 10000 |  |  |  |  | 10000
| BOND |  | 600000 |  | 900000 |  | 1500000
| CDBG | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
| LIQUID FUELS | 290000 | 300000 | 310000 | 320000 | 330000 | 1550000
6. ADA Curb Ramps | SPENDING SCHEDULE | 50000 | 50000 | 50000 | 50000 | 50000 | 250000
FUNDING
| CDBG | 50000 | 50000 | 50000 | 50000 | 50000 | 250000
7. Miscellaneous | SPENDING SCHEDULE | 95000 | 75000 | 75000 | 75000 | 75000 | 395000
Drainage Structures | FUNDING
| BOND 2013 | 95000 |  |  |  |  | 95000
| BOND |  | 150000 |  | 150000 |  | 300000
8. Tree Planting | SPENDING SCHEDULE |  | 10000 | 10000 | 10000 | 10000 | 40000
Program | FUNDING
| CDBG |  | 10000 | 10000 | 10000 | 10000 | 40000
9. Geographic | SPENDING SCHEDULE | 94000 | 50000 | 50000 | 107700 |  | 301700
Information System | FUNDING
| BOND 2013 | 94000 |  |  |  |  | 94000
| BOND |  | 100000 |  | 107700 |  | 207700
10. Aerial Bucket Truck | SPENDING SCHEDULE |  | 150000 |  | 150000 |  | 300000
(2-Replacements) | FUNDING
Electrical Bureau | BOND |  | 150000 |  | 150000 |  | 300000
11. Aerial Bucket Truck | SPENDING SCHEDULE |  |  |  | 150000 |  | 150000
(1-New) for Electrical | FUNDING
Bureau | BOND |  |  |  | 150000 |  | 150000
12. Service Truck (new) | SPENDING SCHEDULE |  | 80000 |  |  |  | 80000
Mechanical Bureau | FUNDING
| BOND |  | 80000 |  |  |  | 80000
13. Mechanical Bureau | SPENDING SCHEDULE |  |  |  | 150000 |  | 150000
Truck Lift | FUNDING
| BOND |  |  |  | 150000 |  | 150000
14. Street Equipment | SPENDING SCHEDULE | 270000 | 275000 | 280000 | 285000 | 290000 | 1400000
FUNDING
| LIQUID FUELS | 270000 | 275000 | 280000 | 285000 | 290000 | 1400000
15. Streets Mack Heavy | SPENDING SCHEDULE |  | 155000 |  |  |  | 155000
Duty Large Dump | FUNDING
Truck | BOND |  | 155000 |  |  |  | 155000
16. Streets Mack Heavy | SPENDING SCHEDULE |  |  |  | 125000 |  | 125000
Duty Medium Dump | FUNDING
Truck | BOND |  |  |  | 125000 |  | 125000
17. Streets Caterpiller | SPENDING SCHEDULE |  | 69000 |  |  |  | 69000
5-Ton Vibratory | FUNDING
Asphalt Paving Roller | LIQUID FUELS |  | 69000 |  |  |  | 69000
18. Streets GMC3500 | SPENDING SCHEDULE |  | 85000 |  |  |  | 85000
Utility Pickup Truck | FUNDING
| LIQUID FUELS |  | 85000 |  |  |  | 85000
19. Streets Caterpiller | SPENDING SCHEDULE |  |  |  | 170000 |  | 170000
Backhoe Loader | FUNDING
| BOND |  |  |  | 170000 |  | 170000
PUBLIC WORKS OTHER PROJECTS |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 5988944 | 3939472 | 1660000 | 2212700 | 1375000 | 15176116
| BOND (2013) | 809000 | 0 | 0 | 0 | 0 | 809000
| BOND (2009) | 10000 | 0 | 0 | 0 | 0 | 10000
| BOND | 0 | 1910000 | 0 | 2042700 | 0 | 3952700
| CDBG | 328682 | 215000 | 160000 | 160000 | 160000 | 1023682
| FEDERAL | 3394992 | 1268203 | 0 | 0 | 0 | 4663195
| STATE | 536044 | 165000 | 0 | 0 | 0 | 701044
| LIQUID FUELS | 560000 | 729000 | 590000 | 605000 | 620000 | 3104000
| OTHER | 350226 | 354769 | 207500 | 0 | 0 | 912495
| TOTALS | 5988944 | 4641972 | 957500 | 2807700 | 780000 | 15176116

## Parks & Pub Prop
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PARKS & PUBLIC PROPERTY
PROJECT
DESCRIPTION |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
1. City Center Improvements | SPENDING SCHEDULE | 122000 | 125000 | 125000 | 100000 | 75000 | 547000
FUNDING
| BOND 2013 | 122000 |  |  |  |  | 122000
| BOND |  | 250000 |  | 175000 |  | 425000
2. Facility Capital Improvement Plan | SPENDING SCHEDULE | 150000 | 100000 |  | 750000 |  | 1000000
FUNDING
| BOND 2013 | 150000 |  |  |  |  | 150000
| BOND |  | 100000 |  | 750000 |  | 850000
3. Fire House Improvements | SPENDING SCHEDULE | 43000 | 50000 | 50000 | 55000 | 55000 | 253000
FUNDING
| BOND 2013 | 43000 |  |  |  |  | 43000
| BOND |  | 100000 |  | 110000 |  | 210000
4. General Pool Improvements | SPENDING SCHEDULE | 124000 | 100000 | 75000 | 125000 | 100000 | 524000
FUNDING
| BOND 2013 | 103000 |  |  |  |  | 103000
| BOND |  | 175000 |  | 225000 |  | 400000
| OTHER | 21000 |  |  |  |  | 21000
5. Mechanical System Upgrades | SPENDING SCHEDULE | 139000 | 125000 | 100000 | 100000 | 100000 | 564000
FUNDING
| BOND 2013 | 139000 |  |  |  |  | 139000
| BOND |  | 225000 |  | 200000 |  | 425000
6. Monocacy Park Improvements | SPENDING SCHEDULE | 104000 |  |  |  |  | 104000
(Johnston Park dam area) | FUNDING
| STATE | 45200 |  |  |  |  | 45200
| COUNTY | 58800 |  |  |  |  | 58800
7. Monocacy Park Improvements | SPENDING SCHEDULE | 218000 |  |  |  |  | 218000
(Illick's Mill area) | FUNDING
| STATE | 98211 |  |  |  |  | 98211
| COUNTY | 119789 |  |  |  |  | 119789
8. Park/Playground Improvements | SPENDING SCHEDULE | 174200 | 175000 | 175000 | 225000 | 225000 | 974200
FUNDING
| BOND |  | 200000 |  | 300000 |  | 500000
| BOND 2013 | 76000 |  |  |  |  | 76000
| CDBG | 98200 | 75000 | 75000 | 75000 | 75000 | 398200
9. Municipal Ice Rink | SPENDING SCHEDULE | 53000 | 37500 | 37500 | 37500 | 37500 | 203000
| BOND |  | 75000 |  | 75000 |  | 150000
| BOND 2013 | 53000 |  |  |  |  | 53000
10. Roof/Safety Code | SPENDING SCHEDULE | 20000 | 50000 | 50000 | 75000 | 75000 | 270000
FUNDING
| BOND 2013 | 20000 |  |  |  |  | 20000
| BOND |  | 100000 |  | 150000 |  | 250000
11. Sand Island Improvements | SPENDING SCHEDULE | 336000 | 50000 | 50000 | 50000 | 50000 | 536000
FUNDING
| BOND |  | 100000 |  | 100000 |  | 200000
| BOND 2013 | 150000 |  |  |  |  | 150000
| COUNTY | 36000 |  |  |  |  | 36000
| STATE | 150000 |  |  |  |  | 150000
12. South Bethlehem Greenway | SPENDING SCHEDULE | 419000 |  |  |  |  | 419000
Pavilion | FUNDING
| BOND 2013 | 75000 |  |  |  |  | 75000
| BOND | [5 empty] | 0
| COUNTY | 172000 |  |  |  |  | 172000
| OTHER | 172000 |  |  |  |  | 172000
13. Eastern Gateway | SPENDING SCHEDULE | 675000 |  |  |  |  | 675000
FUNDING
| FEDERAL | 450000 |  |  |  |  | 450000
| STATE | 225000 |  |  |  |  | 225000
14. Greenway/Saucon Park Ball | SPENDING SCHEDULE | 200000 | 800000 |  |  |  | 1000000
Fields Connections | FUNDING
| STATE | 500000 |  |  |  |  | 500000
| BOND 2013 | 350000 |  |  |  |  | 350000
| OTHER | 150000 |  |  |  |  | 150000
15. Stone Wall Renovations | SPENDING SCHEDULE |  | 50000 | 50000 | 50000 | 50000 | 200000
FUNDING
| BOND |  | 100000 |  | 100000 |  | 200000
16. Vehicle/Equipment | SPENDING SCHEDULE | 40400 |  |  |  |  | 40400
Acquisition/Replacement | FUNDING
| BOND 2013 | 40400 |  |  |  |  | 40400
17. FEMA/PEMA | SPENDING SCHEDULE | 271000 |  |  |  |  | 271000
FUNDING
| FEMA/PEMA | 271000 |  |  |  |  | 271000
PARKS & PUBLIC PROPERTY |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 3088600 | 1662500 | 712500 | 1567500 | 767500 | 7798600
| BOND | 0 | 1425000 | 0 | 2185000 | 0 | 3610000
| BOND 2013 | 1321400 | 0 | 0 | 0 | 0 | 1321400
| CDBG | 98200 | 75000 | 75000 | 75000 | 75000 | 398200
| FEDERAl | 450000 | 0 | 0 | 0 | 0 | 450000
| STATE | 1018411 | 0 | 0 | 0 | 0 | 1018411
| FEMA/PEMA | 271000 | 0 | 0 | 0 | 0 | 271000
| COUNTY | 386589 | 0 | 0 | 0 | 0 | 386589
| OTHER | 343000 | 0 | 0 | 0 | 0 | 343000
| TOTALS | 3888600 | 1500000 | 75000 | 2260000 | 75000 | 7798600

## C & ED
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
COMMUNITY & ECONOMIC DEVELOPMENT
PROJECT |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
DESCRIPTION
5. Shredding Truck | SPENDING SCHEDULE |  | 235000 |  |  |  | 235000
Recycling | FUNDING
| STATE |  | 235000 |  |  |  | 235000
COMMUNITY AND ECONOMIC DEVEL. |  | 2014 | 2015 | 2016 | 2017 |  | TOTAL
| SPENDING SCHEDULE | 0 | 235000 | 0 | 0 | 0 | 235000
| STATE | 0 | 235000 | 0 | 0 | 0 | 235000
| TOTALS | 0 | 235000 | 0 | 0 | 0 | 235000

## Admin
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
ADMINISTRATION
PROJECT |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
DESCRIPTION
1. IT Improvement Plan | SPENDING SCHEDULE |  | 128000 |  |  |  | 128000
FUNDING
| BOND |  | 128000 |  |  |  | 128000
Administration |  | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
| SPENDING SCHEDULE | 0 | 128000 | 0 | 0 | 0 | 128000
FUNDING
| BOND | 0 | 128000 | 0 | 0 | 0 | 128000
| TOTALS | 0 | 128000 | 0 | 0 | 0 | 128000