## SUMSHEET
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
SUMMARY SHEET
(2018-2022)
| FUNDING | 2018 | 2019 | 2020 | 2021 | 2022 | TOTALS
BOND (2013) | BOND (2013) | 314700 | 0 | 0 | 0 | 0 | 314700
| BOND (2015) | 292200 | 0 | 0 | 0 | 0 | 292200
| BOND (2017) | 3604644 | 460000 | 0 | 460000 | 0 | 4524644
BOND (2017) | BOND | 0 | 9539336 | 0 | 7810000 | 0 | 17349336
| CDBG (2016) | 37500 | 0 | 0 | 0 | 0 | 37500
| CDBG (2017) | 246616 | 0 | 0 | 0 | 0 | 246616
| CDBG (2018) | 500000 | 475000 | 375000 | 532000 | 429000 | 2311000
| FEDERAL | 600000 | 700000 | 1100000 | 1200000 | 0 | 3600000
| STATE | 962500 | 0 | 0 | 0 | 0 | 962500
FEMA | FEMA GRANT | 285000 | 0 | 0 | 0 | 0 | 285000
| LIQUID FUELS | 1768704 | 883000 | 1066000 | 350000 | 360000 | 4427704
| OTHER | 1036250 | 1646362 | 1385000 | 2913181 | 2485000
| TOTALS | 9648114 | 13703698 | 3926000 | 13265181 | 3274000 | 43816993
| SPENDING | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SCHEDULE | 9423114 | 10703017 | 7001681 | 9882681 | 6806500 | 43816993
LAST REVISED 09/18/17

## Public Safety
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE 2018-2022
PUBLIC SAFETY
PROJECT |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
DESCRIPTION
1. Ambulance Replacement/Remount Plan | SPENDING SCHEDULE | 135000 | 135000 | 135000 | 135000 | 135000 | 675000
FUNDING
| BOND | 0 | 135000 | 0 | 135000 |  | 270000
| OTHER CDBG | 135000 | 0 | 135000 | 0 | 135000 | 405000
2. Fire Apparatus Replacement Plan | SPENDING SCHEDULE | 297183 | 0 | 0 | 0 | 0 | 297183
Ladder Truck Aerial Tower | FUNDING
| BOND 2017 | 297183 | 0 | 0 | 0 | 0 | 297183
3. Fire Apparatus Replacement Plan - | SPENDING SCHEDULE | 0 | 363181 | 363181 | 363181 |  | 1089543
Quint Ladder Truck | FUNDING
| OTHER | 0 | 726362 | 0 | 363181 | 0 | 1089543
4. Fire Apparatus Replacement Plan - | SPENDING SCHEDULE | 0 | 165000 | 165000 | 165000 | 165000 | 660000
Rescue Engine Replacement | FUNDING
| BOND | 0 | 330000 | 0 | 330000 | 0 | 660000
5. Self-Contained Breathing Apparatus | SPENDING SCHEDULE | 580967 | 100000 | 0 | 0 | 0 | 680967
Replacement Plan | FUNDING
| BOND | 0 | 100000 | 0 | 0 | 0 | 100000
| BOND 2017 | 295967 | 0 | 0 | 0 | 0 | 295967
| FEMA GRANT | 285000 | 0 | 0 | 0 | 0 | 285000
6. Body Cameras | SPENDING SCHEDULE | 0 | 40000 | 35000 | 40000 | 35000 | 150000
FUNDING
| BOND | 0 | 75000 | 0 | 75000 | 0 | 150000
| BOND 2017 | 0 | 0 | 0 | 0 | 0 | 0
7. Fire Apparatus Replacement Plan- | SPENDING SCHEDULE | 0 | 145000 | 145000 | 145000 | 145000 | 580000
Engine Replacement #1 | FUNDING
| BOND | 0 | 290000 | 0 | 290000 | 0 | 580000
8. Fire Apparatus Replacement Plan- | SPENDING SCHEDULE | 0 | 0 | 0 | 145000 | 145000 | 290000
Engine Replacement #2 | FUNDING
| BOND | 0 | 0 | 0 | 290000 | 0 | 290000
PUBLIC SAFETY |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 1013150 | 948181 | 843181 | 993181 | 625000 | 4422693
FUNDING
| BOND | 0 | 930000 | 0 | 1120000 | 0 | 2050000
| BOND 2017 | 593150 | 0 | 0 | 0 | 0 | 593150
| OTHER | 135000 | 726362 | 135000 | 363181 | 135000 | 1494543
| FEMA GRANT | 285000 | 0 | 0 | 0 | 0 | 285000
| TOTALS | 1013150 | 1656362 | 135000 | 1483181 | 135000 | 4422693

## P W Traffic
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - TRAFFIC
PROJECT |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
DESCRIPTION
1. TR/Isolated Intersections | SPENDING SCHEDULE | 388896 | 320000 | 40000 | 320000 | 40000 | 1108896
FUNDING
| BOND (2017) | 388896 | 360000 | 0 | 360000 | 0 | 1108896
2. TR/Traffic Safety Imprv. | SPENDING SCHEDULE | 70000 | 50000 | 50000 | 50000 | 50000 | 270000
FUNDING
| BOND (2017) | 70000 | 100000 | 0 | 100000 | 0 | 270000
3. Route 412 Lighting | SPENDING SCHEDULE | 0 | 150000 | 0 | 0 | 0 | 150000
Upgrade | FUNDING
| BOND | 0 | 150000 | 0 | 0 | 0 | 150000
PUBLIC WORKS -TRAFFIC |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 458896 | 520000 | 90000 | 370000 | 90000 | 1528896
FUNDING
| BOND | 0 | 150000 | 0 | 0 | 0 | 150000
| BOND (2017) | 458896 | 460000 | 0 | 460000 | 0 | 1378896
| TOTALS | 458896 | 610000 | 0 | 460000 | 0 | 1528896

## P W Streets
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - STREETS
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. Carlton Avenue | SPENDING SCHEDULE | 265000 | 265000 | 265000 | 0 | 0 | 795000
Broadway to Summit St. | FUNDING
| CDBG | 265000 | 265000 | 265000 | 0 | 0 | 795000
2. West Garrison Street | SPENDING SCHEDULE | 75000 | 0 | 0 | 0 | 0 | 75000
Main Street to N. New Street | FUNDING
| BOND (2017) | 75000 | 0 | 0 | 0 | 0 | 75000
3. City Hall Complex Parking | SPENDING SCHEDULE | 140000 | 0 | 0 | 0 | 0 | 140000
Lay-bys Reconstruction | FUNDING
Phase III | BOND (2017) | 140000 | 0 | 0 | 0 | 0 | 140000
4. New Street - 3rd to 4th Streets | SPENDING SCHEDULE | 80000 | 0 | 0 | 0 | 0 | 80000
(Turnback project) | FUNDING
| OTHER | 80000 | 0 | 0 | 0 | 0 | 80000
5. Public Works Engineering | SPENDING SCHEDULE | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
Costs for CDBG Eligible | FUNDING
Street Projects | CDBG | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
6. West Broad Street | SPENDING SCHEDULE | 0 | 50000 | 0 | 0 | 0 | 50000
(Mangan Street west to old Coke | FUNDING
Plant-curb and sidewalk) | OTHER | 0 | 50000 | 0 | 0 | 0 | 50000
7. Fourth Avenue | SPENDING SCHEDULE | 0 | 0 | 50000 | 0 | 0 | 50000
Prospect Ave. to Kichline St. | FUNDING
| OTHER | 0 |  | 50000 | 0 | 0 | 50000
8. Lehigh Way | SPENDING SCHEDULE | 60000 | 0 | 0 | 0 | 0 | 60000
FUNDING
| BOND (2017) | 60000 | 0 | 0 | 0 | 0 | 60000
9. West Packer Ave | SPENDING SCHEDULE | 0 | 0 | 0 | 322000 | 0 | 322000
Montclair Ave to Brodhead Ave | FUNDING
| CDBG | 0 | 0 | 0 | 322000 | 0 | 322000
10. West Packer Ave | SPENDING SCHEDULE | 0 | 0 | 0 | 0 | 219000 | 219000
Carlton to Montclair | FUNDING
| CDBG | 0 | 0 | 0 | 0 | 219000 | 219000
11. Street Overlay | SPENDING SCHEDULE | 1321168 | 740000 | 950000 | 1050000 | 1060000 | 5121168
Program | FUNDING
| BOND | 0 | 1000000 | 0 | 1400000 |  | 2400000
| BOND (2017) | 474135 | 0 | 0 | 0 | 0 | 474135
| CDBG (2017) | 101179 | 0 | 0 | 0 | 0 | 101179
| CDBG (2018) | 25000 | 0 | 0 | 0 | 0 | 25000
| LIQUID FUELS | 720854 | 340000 | 350000 | 350000 | 360000 | 2120854
12. Streets Mack Heavy | SPENDING SCHEDULE | 0 | 195000 | 0 | 0 | 0 | 195000
Duty Medium Dump | FUNDING
Truck | BOND | 0 | 195000 | 0 | 0 | 0 | 195000
| LIQUID FUELS | 0 | 0 | 0 | 0 | 0 | 0
13. Streets Leaf Loaders | SPENDING SCHEDULE | 0 | 76000 | 76000 | 0 | 0 | 152000
ODB Extreme Vac- | FUNDING |  |  |  |  | 0
Model SCL65TM5 | BOND | 0 | 76000 | 0 | 0 | 0 | 76000
| LIQUID FUELS | 0 | 0 | 76000 | 0 | 0 | 76000
14. Caterpillar Model | SPENDING SCHEDULE | 0 | 0 | 0 | 195000 | 0 | 195000
930M Wheel Loader | FUNDING
| BOND | 0 | 0 | 0 | 195000 | 0 | 195000
15. John Deere Model | SPENDING SCHEDULE | 0 | 230000 | 0 | 0 | 0 | 230000
624K Wheel Loader | FUNDING
| BOND | 0 | 230000 | 0 | 0 | 0 | 230000
16. GMC Pickup Trucks | SPENDING SCHEDULE | 70000 | 73000 | 0 | 0 | 0 | 143000
FUNDING
| LIQUID FUELS | 70000 | 73000 | 0 | 0 | 0 | 143000
17. GMC Small Dump Truck | SPENDING SCHEDULE | 120000 | 0 | 0 | 0 | 0 | 120000
FUNDING
| LIQUID FUELS | 120000 | 0 | 0 | 0 | 0 | 120000
18. 2018 P385B Weiler Track | SPENDING SCHEDULE | 212000 | 0 | 0 | 0 | 0 | 212000
Asphalt Paver | FUNDING
| LIQUID FUELS | 212000 | 0 | 0 | 0 | 0 | 212000
19. Elgin Pelican | SPENDING SCHEDULE | 0 | 230000 | 240000 | 0 | 0 | 470000
Broom Sweepers | FUNDING
| LIQUID FUELS | 0 | 230000 | 240000 | 0 | 0 | 470000
20. Kodiak Model LMSSC3036 | SPENDING SCHEDULE | 0 | 165000 | 0 | 0 | 0 | 165000
Snow Blower for 624K | FUNDING
Wheel Loader | BOND | 0 | 165000 | 0 | 0 | 0 | 165000
21. Aqua Tech B-10 Vac Truck | SPENDING SCHEDULE | 0 | 303336 | 0 | 0 | 0 | 303336
FUNDING
| BOND | 0 | 303336 | 0 | 0 | 0 | 303336
PUBLIC WORKS - STREETS |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 2353168 | 2337336 | 1591000 | 1577000 | 1289000 | 9147504
FUNDING
| BOND | 0 | 1969336 | 0 | 1595000 | 0 | 3564336
| BOND (2017) | 749135 | 0 | 0 | 0 | 0 | 749135
| CDBG (2017) | 101179 | 0 | 0 | 0 | 0 | 101179
| CDBG (2018) | 300000 | 275000 | 275000 | 332000 | 229000 | 1411000
| OTHER | 80000 | 50000 | 50000 | 0 | 0 | 180000
| LIQUID FUELS | 1122854 | 643000 | 666000 | 350000 | 360000 | 3141854
| TOTALS | 2353168 | 2937336 | 991000 | 2277000 | 589000 | 9147504

## P W Storm Sewers
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - STORM SEWERS
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. West Broad St | SPENDING SCHEDULE | 200000 | 0 | 0 | 0 | 0 | 200000
1st Ave to 2nd Ave | FUNDING
| LIQUID FUELS | 200000 | 0 | 0 | 0 | 0 | 200000
2. West Laurel Street to | SPENDING SCHEDULE | 225000 | 0 | 0 | 0 | 0 | 225000
the Monocacy Creek | FUNDING
| LIQUID FUELS | 78750 | 0 | 0 | 0 | 0 | 78750
| OTHER (MORAV COL) | 146250 | 0 | 0 | 0 | 0 | 146250
3. Linden Street Storm | SPENDING SCHEDULE | 229000 | 0 | 0 | 0 | 0 | 229000
Sewer Upgrade/Repl. | FUNDING
| LIQUID FUELS | 33100 | 0 | 0 | 0 | 0 | 33100
| BOND (2013) | 34700 | 0 | 0 | 0 | 0 | 34700
| BOND (2015) | 161200 | 0 | 0 | 0 | 0 | 161200
4. Standford Rd - Storm Sewer Extension | SPENDING SCHEDULE | 100000 | 0 | 0 | 0 | 0 | 100000
FUNDING
| LIQUID FUELS | 100000 | 0 | 0 | 0 | 0 | 100000
5. East Boulevard | SPENDING SCHEDULE | 234000 | 0 | 0 | 0 | 0 | 234000
Boyd Street Southwardly | FUNDING
to Landsdale Avenue | LIQUID FUELS | 234000 | 0 | 0 | 0 | 0 | 234000
6. Old Brick Sewer on Broadway - | SPENDING SCHEDULE | 0 | 0 | 200000 | 0 | 0 | 200000
Jischke St to 3rd St | FUNDING
| LIQUID FUELS | 0 | 0 | 200000 | 0 | 0 | 200000
7. Millside Drive & Traveller Avenue - | SPENDING SCHEDULE | 0 | 120000 | 0 | 0 | 0 | 120000
Drainage Improvements | FUNDING
| LIQUID FUELS | 0 | 120000 | 0 | 0 | 0 | 120000
8. Stefko Drainage Swale | SPENDING SCHEDULE | 0 | 0 | 1000000 | 250000 | 0 | 1250000
FUNDING
| LIQUID FUELS | 0 | 0 | 200000 | 0 | 0 | 200000
| OTHER | 0 | 0 | 800000 | 250000 | 0 | 1050000
9. West Goepp Street - | SPENDING SCHEDULE | 0 | 0 | 250000 | 0 | 0 | 250000
Masslich Street to New Street | FUNDING
| OTHER | 0 | 0 | 250000 | 0 | 0 | 250000
10. Fifth Street - Buchanan to | SPENDING SCHEDULE | 0 | 220000 | 0 | 0 | 0 | 220000
Fillmore Street | FUNDING
| OTHER | 0 | 220000 | 0 |  | 0 | 220000
11. Creek Road Culvert Repl. | SPENDING SCHEDULE | 0 | 0 | 0 | 0 | 200000 | 200000
FUNDING
| OTHER | 0 | 0 | 0 | 0 | 200000 | 200000
12. Johnston Drive | SPENDING SCHEDULE | 0 | 0 | 0 | 0 | 1000000 | 1000000
Swale Improvements | FUNDING
| OTHER | 0 | 0 | 0 | 0 | 1000000 | 1000000
13. Easton Ave to Stefko Blvd | SPENDING SCHEDULE | 0 | 0 | 0 | 1900000 | 1000000 | 2900000
Storm Sewer System upgrades | FUNDING
- various locations Phase I&II | OTHER | 0 | 0 | 0 | 1900000 | 1000000 | 2900000
14. Miscellaneous | SPENDING SCHEDULE | 118650 | 87500 | 87500 | 87500 | 87500 | 468650
Drainage Structures | FUNDING
| BOND (2017) | 118650 | 0 | 0 | 0 | 0 | 118650
| BOND | 0 | 175000 | 0 | 175000 | 0 | 350000
15. W. North Street Storm Sewer | SPENDING SCHEDULE | 0 | 120000 | 0 | 0 | 0 | 120000
Replacement | FUNDING
| LIQUID FUELS | 0 | 120000 | 0 | 0 | 0 | 120000
PUBLIC WORKS - STORM SEWERS |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 1106650 | 547500 | 1537500 | 2237500 | 2287500 | 7716650
FUNDING
| BOND | 0 | 175000 | 0 | 175000 | 0 | 350000
| BOND (2013) | 34700 | 0 | 0 | 0 | 0 | 34700
| BOND (2015) | 161200 | 0 | 0 | 0 | 0 | 161200
| BOND (2017) | 118650 | 0 | 0 | 0 | 0 | 118650
| LIQUID FUELS | 645850 | 240000 | 400000 | 0 | 0 | 1285850
| OTHER | 146250 | 220000 | 1050000 | 2150000 | 2200000 | 5766250
| TOTALS | 1106650 | 635000 | 1450000 | 2325000 | 2200000 | 7716650

## PW Facilities
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - FACILITIES
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. Facilities Capital Improvement | SPENDING SCHEDULE | 0 | 400000 | 400000 | 400000 | 400000 | 1600000
FUNDING
| BOND | 0 | 800000 | 0 | 800000 | 0 | 1600000
2. Rodgers Street Maintenance Facility | SPENDING SCHEDULE | 0 | 0 | 0 | 350000 | 350000 | 700000
Replacement | FUNDING
| BOND | 0 | 0 | 0 | 700000 | 0 | 700000
3. City Emergency Service Facility | SPENDING SCHEDULE | 0 | 40000 | 160000 | 0 | 0 | 200000
FUNDING
| BOND | 0 | 200000 | 0 | 0 | 0 | 200000
4. City Center Improvements | SPENDING SCHEDULE | 162102 | 200000 | 200000 | 400000 | 350000 | 1312102
FUNDING
| BOND | 0 | 400000 | 0 | 750000 | 0 | 1150000
| BOND (2017) | 162102 | 0 | 0 | 0 | 0 | 162102
5. Fan Coil Replacements | SPENDING SCHEDULE | 0 | 180000 | 0 | 0 | 0 | 180000
FUNDING
| BOND | 0 | 180000 | 0 | 0 | 0 | 180000
6. Chiller Replacement | SPENDING SCHEDULE | 0 | 180000 | 0 | 0 | 0 | 180000
FUNDING
| BOND | 0 | 180000 | 0 | 0 | 0 | 180000
7. City Hall Plaza Drainage Pipe | SPENDING SCHEDULE | 0 | 0 | 0 | 100000 | 0 | 100000
Replacement | FUNDING
| BOND | 0 | 0 | 0 | 100000 | 0 | 100000
8. Superior Boiler Replacement | SPENDING SCHEDULE | 0 | 0 | 0 | 200000 | 0 | 200000
| FUNDING | [5 empty] | 0
| BOND | 0 | 0 | 0 | 200000 | 0 | 200000
9. Police Forensics and DUI Area | SPENDING SCHEDULE | 0 | 80000 | 0 | 0 | 0 | 80000
Heat Pump System | FUNDING | [5 empty] | 0
| BOND | 0 | 80000 | 0 | 0 | 0 | 80000
10. Library Exterior Column Repair | SPENDING SCHEDULE | 0 | 400000 | 0 | 400000 | 0 | 800000
FUNDING
| BOND | 0 | 400000 | 0 | 400000 | 0 | 800000
11. City Hall Garage Structural | SPENDING SCHEDULE | 0 | 200000 | 0 | 0 | 0 | 200000
Concrete Repair | FUNDING
| BOND | 0 | 200000 | 0 | 0 | 0 | 200000
12. City Hall Garage Floor Repair | SPENDING SCHEDULE | 0 | 200000 | 200000 | 200000 | 200000 | 800000
FUNDING
| BOND | 0 | 400000 | 0 | 400000 | 0 | 800000
13. Domestic Water Tank Repl. | SPENDING SCHEDULE | 0 | 110000 | 0 | 0 | 0 | 110000
FUNDING
| BOND | 0 | 110000 | 0 | 0 | 0 | 110000
14. Fire House Improvements | SPENDING SCHEDULE | 60000 | 50000 | 40000 | 40000 | 50000 | 240000
FUNDING
| BOND (2017) | 60000 | 0 | 0 | 0 | 0 | 60000
| BOND | 0 | 90000 | 0 | 90000 | 0 | 180000
15. Roof/Safety/Code Requirements | SPENDING SCHEDULE | 50000 | 120000 | 120000 | 120000 | 120000 | 530000
FUNDING
| BOND (2017) | 50000 | 0 | 0 | 0 | 0 | 50000
| BOND | 0 | 240000 | 0 | 240000 | 0 | 480000
PUBLIC WORKS - FACILITIES |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 272102 | 2160000 | 1120000 | 2210000 | 1470000 | 7232102
| BOND (2017) | 272102 | 0 | 0 | 0 | 0 | 272102
| BOND | 0 | 3280000 | 0 | 3680000 | 0 | 6960000
| TOTALS | 272102 | 3280000 | 0 | 3680000 | 0 | 7232102

## PW Grounds
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - GROUNDS
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. Grounds Capital Improvements | SPENDING SCHEDULE | 301148 | 175000 | 175000 | 175000 | 175000 | 1001148
FUNDING
| BOND | 0 | 150000 | 0 | 150000 | 0 | 300000
| BOND (2017) | 55711 | 0 | 0 | 0 | 0 | 55711
| CDBG (2013-2017) | 145437 | 0 | 0 | 0 | 0 | 145437
| CDBG (2018) | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
2. Greenway/Saucon Park | SPENDING SCHEDULE | 880000 | 0 | 0 | 0 | 0 | 880000
Ballfield Connections | FUNDING
| STATE | 450000 | 0 | 0 | 0 | 0 | 450000
| BOND (2013) | 280000 | 0 | 0 | 0 | 0 | 280000
| OTHER | 150000 | 0 | 0 | 0 | 0 | 150000
3. Vehicle/Equipment | SPENDING SCHEDULE | 0 | 0 | 0 | 250000 | 0 | 250000
Acquisition/Replacement | FUNDING
(Garbage Truck) | BOND | 0 | 0 | 0 | 250000 | 0 | 250000
4. Greenway - | SPENDING SCHEDULE | 400000 | 0 | 0 | 0 | 0 | 400000
Plaza Development | FUNDING
| STATE | 200000 | 0 | 0 | 0 | 0 | 200000
| OTHER | 200000 | 0 | 0 | 0 | 0 | 200000
PUBLIC WORKS - GROUNDS
|  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 1581148 | 175000 | 175000 | 425000 | 175000 | 2531148
FUNDING
| BOND (2013) | 280000 | 0 | 0 | 0 | 0 | 280000
| BOND (2017) | 55711 | 0 | 0 | 0 | 0 | 55711
| BOND | 0 | 150000 | 0 | 400000 | 0 | 550000
| CDBG (2017) | 145437 | 0 | 0 | 0 | 0 | 145437
| CDBG (2018) | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
| STATE | 650000 | 0 | 0 | 0 | 0 | 650000
| OTHER | 350000 | 0 | 0 | 0 | 0 | 350000
| TOTALS | 1581148 | 250000 | 100000 | 500000 | 100000 | 2531148

## P W Other
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
PUBLIC WORKS - OTHER PROJECTS
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. Lynn Ave. Bridge | SPENDING SCHEDULE | 750000 | 0 | 0 | 0 | 0 | 750000
FUNDING
| CDBG | 0 | 0 | 0 | 0 | 0 | 0
| CDBG (2016) | 37500 | 0 | 0 | 0 | 0 | 37500
| FEDERAL | 600000 | 0 | 0 | 0 | 0 | 600000
| STATE | 112500 | 0 | 0 | 0 | 0 | 112500
2. W Broad St Lighting | SPENDING SCHEDULE | 285000 | 0 | 0 | 0 | 0 | 285000
3rd Ave to 5th Ave | FUNDING
| BOND (2017) | 85000 | 0 | 0 | 0 | 0 | 85000
| STATE | 200000 | 0 | 0 | 0 | 0 | 200000
3. Bridge Repairs | SPENDING SCHEDULE | 191000 | 70000 | 70000 | 70000 | 70000 | 471000
FUNDING
| BOND | 0 | 140000 | 0 | 140000 | 0 | 280000
| BOND (2015) | 51000 | 0 | 0 | 0 | 0 | 51000
| BOND (2017) | 140000 | 0 | 0 | 0 | 0 | 140000
4. Route 378 Pole | SPENDING SCHEDULE | 0 | 700000 | 400000 |  | 0 | 1100000
Replacement | FUNDING
| BOND | 0 | 0 | 0 | 0 | 0 | 0
| FED/STATE | 0 | 700000 | 400000 | 0 | 0 | 1100000
5. Geographic | SPENDING SCHEDULE | 80000 | 0 | 0 | 0 | 0 | 80000
Information System | FUNDING
| BOND (2015) | 80000 | 0 | 0 | 0 | 0 | 80000
6. Citywide Wayfinding | SPENDING SCHEDULE | 100000 | 0 | 0 | 0 | 0 | 100000
Signage | FUNDING
| BOND (2017) | 100000 | 0 | 0 | 0 | 0 | 100000
7. Aerial Bucket Truck | SPENDING SCHEDULE | 0 | 150000 | 0 | 0 | 0 | 150000
Electrical Bureau | FUNDING
| BOND | 0 | 150000 | 0 | 0 | 0 | 150000
8. Service Truck (new) | SPENDING SCHEDULE | 0 | 80000 | 0 | 0 | 0 | 80000
Mechanical Bureau | FUNDING
| BOND | 0 | 80000 | 0 | 0 | 0 | 80000
9. Mechanical Bureau- | SPENDING SCHEDULE | 0 | 75000 | 0 | 0 | 0 | 75000
Replacement of Garage | FUNDING
Doors | BOND | 0 | 75000 | 0 | 0 | 0 | 75000
10. Flood Control System | SPENDING SCHEDULE | 0 | 0 | 600000 | 1200000 | 0 | 1800000
FUNDING
| FEDERAL | 0 | 0 | 600000 | 1200000 | 0 | 1800000
11. Portable Radios | SPENDING SCHEDULE | 0 | 340000 | 0 | 0 | 0 | 340000
FUNDING
| BOND | 0 | 340000 | 0 | 0 | 0 | 340000
PUBLIC WORKS - OTHER PROJECTS |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 1406000 | 1415000 | 1070000 | 1270000 | 70000 | 5231000
| BOND (2017) | 325000 | 0 | 0 | 0 | 0 | 325000
| BOND (2015) | 131000 | 0 | 0 | 0 | 0 | 131000
| BOND | 0 | 785000 | 0 | 140000 | 0 | 925000
| CDBG (2016) | 37500 | 0 | 0 | 0 | 0 | 37500
| CDBG (2017) | 0 | 0 | 0 | 0 | 0 | 0
| FEDERAL | 600000 | 700000 | 1000000 | 1200000 | 0 | 3500000
| STATE | 312500 | 0 | 0 | 0 | 0 | 312500
| TOTALS | 1406000 | 1485000 | 1000000 | 1340000 | 0 | 5231000

## Recreation
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
RECREATION
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. General Pool Improvements | SPENDING SCHEDULE | 59000 | 50000 | 50000 | 50000 | 50000 | 259000
FUNDING
| BOND 2017 | 59000 | 0 | 0 | 0 | 0 | 59000
| BOND | 0 | 100000 | 0 | 100000 | 0 | 200000
2. Municipal Ice Rink | SPENDING SCHEDULE | 100000 | 100000 | 100000 | 50000 | 50000 | 400000
FUNDING
| BOND | 0 | 200000 | 0 | 100000 | 0 | 300000
| BOND 2017 | 100000 | 0 | 0 | 0 | 0 | 100000
3. Memorial Pool Project | SPENDING SCHEDULE | 87000 | 2000000 | 0 | 200000 | 200000 | 2487000
Complex Improvements | FUNDING
| BOND | 0 | 1500000 | 0 | 0 | 0 | 1500000
| BOND 2017 | 87000 | 0 | 0 | 0 | 0 | 87000
| OTHER | 0 | 500000 | 0 | 400000 | 0 | 900000
4. Neighborhood Pool Conversion | SPENDING SCHEDULE | 0 | 0 | 0 | 100000 | 100000 | 200000
FUNDING
| BOND | 0 | 0 | 0 | 200000 | 0 | 200000
5. Parks System Master Plan | SPENDING SCHEDULE | 176000 | 0 | 0 | 0 | 0 | 176000
FUNDING
| BOND 2017 | 176000 | 0 | 0 | 0 | 0 | 176000
RECREATION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 422000 | 2150000 | 150000 | 400000 | 400000 | 3522000
| BOND 2017 | 422000 | 0 | 0 | 0 | 0 | 422000
| BOND | 0 | 1800000 | 0 | 400000 | 0 | 2200000
| OTHER | 0 | 500000 | 0 | 400000 | 0 | 900000
| TOTALS | 422000 | 2300000 | 0 | 800000 | 0 | 3522000

## Admin
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
ADMINISTRATION
PROJECT |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
DESCRIPTION
1. IT Improvement Plan | SPENDING SCHEDULE | 260000 | 0 | 0 | 0 | 0 | 260000
FUNDING
| BOND (2017) | 260000 | 0 | 0 | 0 | 0 | 260000
ADMINISTRATION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 260000 | 0 | 0 | 0 | 0 | 260000
FUNDING
| BOND (2017) | 260000 | 0 | 0 | 0 | 0 | 260000
| TOTALS | 260000 | 0 | 0 | 0 | 0 | 260000

## CED
CITY OF BETHLEHEM
NON UTILITY CAPITAL IMPROVEMENT PROGRAM
FUNDING/SPENDING SCHEDULE
DEPARTMENT OF COMMUNITY AND ECONOMIC DEVELOPMENT
PROJECT
DESCRIPTION |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
1. Blighted Property Acquisition | SPENDING SCHEDULE | 550000 | 450000 | 425000 | 400000 | 400000 | 2225000
FUNDING
| BOND 2017 | 350000 | 0 | 0 | 0 | 0 | 350000
| BOND | 0 | 300000 | 0 | 300000 | 0 | 600000
| CDBG | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
| OTHER | 325000 | 150000 | 150000 | 0 | 150000 | 775000
C&ED |  | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
| SPENDING SCHEDULE | 550000 | 450000 | 425000 | 400000 | 400000 | 2225000
FUNDING
| BOND 2017 | 350000 | 0 | 0 | 0 | 0 | 350000
| BOND | 0 | 300000 | 0 | 300000 | 0 | 600000
| CDBG | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
| OTHER | 325000 | 150000 | 150000 | 0 | 150000 | 775000
| TOTALS | 775000 | 550000 | 250000 | 400000 | 250000 | 2225000